PROJECT MANAGEMENT BRIEF

BASELINE-ALIGNED DELIVERY WORKPLAN

Controlled route to deliver OT Digital Twin as specified, without scope creep

| Plan date | 27 May 2026 (East Africa Time) |
| --- | --- |
| Prepared for | OTDT Project Manager and Delivery Team |
| Target product | GDC Kenya Geothermal Digital Twin MVP |
| Planning basis | Three controlling OTDT artifacts plus verified current-state assessment |
| Control rule | No product fact, acceptance target or demo narrative changes without recorded approval |

DELIVERY OBJECTIVE Deliver the documented OTDT MVP: a synthetic-data GDC Kenya digital twin of 50 assets, centred on GDC-WP-007, using Unity and Three.js visualisation with five defined agent capabilities, the approved 34% to 68% What-If story, a validated 90-day schedule and top-five work-order output.

# 1. Scope Control Charter

All delivery activity must observe the following controls:

- The governing product definition is the three project-owner supplied root artifacts: the Build Guide DOCX, Build Deck PPTX and MVP Tracker XLSX.

- The supplied tracker data is the baseline synthetic data package. Derived datasets may be used only after lineage, transformation and purpose are explicitly documented.

- Required product identity is fixed: GDC Kenya, 50 assets, GDC-WP-007, five agents, Unity plus Three.js, and the approved ROI scenario.

- Any implementation addition such as React, Redis, TimescaleDB, extra dashboards or conversational panels is supporting implementation unless explicitly promoted by an approved decision.

- No team member may label a capability implemented, validated, deployed or accepted on the basis of file existence alone; evidence must be recorded.

- IBM platform execution remains paused until the project manager explicitly reactivates it; the IBM requirements remain in scope.

# 2. Definition Of MVP Acceptance

| Acceptance domain | Acceptance condition |
| --- | --- |
| Experience | Unity primary digital twin demonstrates sensor state, asset selection, WP-07 What-If and schedule; Three.js browser viewer is available for browser access. |
| Assets and data | 50 GDC assets and approved sensor/failure/validation datasets flow through documented contracts with synthetic-data labelling. |
| Failure Predictor | Approved LSTM specification is implemented and evidenced above AUC-ROC 0.82 with calibration and deployment artifact evidence. |
| Monte Carlo | Tracker-derived fitting and validation are documented; 10,000 scenarios complete under 5 seconds; validation reaches Brier score below 0.15. |
| What-If | For WP-07, the visible user path shows 34% at zero days and 68% / USD 122,400 at 45 days in less than 2 seconds. |
| Anomaly AI | CNN achieves greater than 80% accuracy, or the explicitly permitted rule-based MVP fallback is demonstrated and labelled as such. |
| Scheduler | 90-day schedule identifies the required high-risk decisions and exposes top-five Maximo work-order output within approved mock/live mode. |
| Demo and ROI | Stakeholder demonstration tells the fixed synthetic-data narrative and retains the approved USD 360,000 versus USD 48,000 / 650% ROI statement. |

# 3. Delivery Sequence And Gates

Work is organised as gated steps. A later step may begin in limited preparation mode, but it may not be reported complete until its dependencies and exit gate are complete.

| Step | Work package | Required outputs and evidence | Exit gate |
| --- | --- | --- | --- |
| 0 | Confirm authority and resolve product decisions | Approved authority list; decisions on Sensor_Readings count, failure-mode grouping, WP-07 cost policy, LSTM run specification and IBM hold. | Decision log updated; no unresolved decision is silently encoded in product behaviour. |
| 1 | Establish canonical data and API contracts | Dataset lineage map; baseline sensor schema; canonical asset/cost handling; What-If request/response contract; contract tests. | Runtime consumes approved data/contracts; WP-07 API test gives 34% and 68% / USD 122,400. |
| 2 | Restore Unity primary demonstration | Unity scene verification for all 50 assets, selectable WP-07, sensor colour updates, HUD, disclaimer, slider and cost overlay. | Recorded play-mode evidence; 45-day visible scenario works in under 2 seconds. |
| 3 | Validate LSTM and Monte Carlo engines | Approved LSTM pipeline, AUC/calibration evidence, exported artifact; fitted Weibull parameters, Brier validation and performance benchmark. | Model and simulation acceptance thresholds met or explicitly approved fallback used. |
| 4 | Deliver scheduler and work-order story | Risk feed into scheduler; 90-day Gantt; top-five WO contract; controlled mock Maximo integration. | Scenario 3 reproduces intended highlighted risks and schedule evidence. |
| 5 | Complete browser viewer and Anomaly AI | Three.js viewer with sensor colours/navigation; CNN evidence or labelled rule-based fallback. | Both required experience channel and anomaly requirement demonstrable. |
| 6 | Reactivate IBM integrations when authorised | Maximo, Watson/Watson Studio, Event Streams, OpenShift and API Connect verification evidence. | Project-manager approval to resume plus environment test evidence. |
| 7 | End-to-end acceptance and demo handover | Acceptance results pack, demo runbook, risk/decision closure list, deployment proposal. | Project-manager sign-off for stakeholder demonstration. |

# 4. Step-By-Step Work Packages

## Step 0: Baseline Lock And Decisions

Purpose: remove ambiguity before coding turns undocumented assumptions into product behaviour.

| Action | Owner role | Evidence to retain |
| --- | --- | --- |
| Confirm the three governing files and correct the repository authority references. | Project manager / product owner | Approved decision log entry. |
| Decide Sensor_Readings dataset interpretation and publish the approved training source. | Product owner with AI/ML lead | Row-count decision and dataset checksum/reference. |
| Approve failure-mode aggregation used for Weibull fitting. | Product owner with reliability/ML lead | Mapping table from physical labels to fitted groups. |
| Approve WP-07 cost treatment and how USD 180,000 relates to asset inventory values. | Project manager / business owner | Cost rule used in UI, scheduler and ROI narrative. |
| Choose approved LSTM source-faithful experiment specification. | Product owner with AI/ML lead | Decision entry stating permitted features/split/export requirements. |

## Step 1: Contract And Data Foundation

Purpose: create one controlled foundation used by Unity, model services, scheduler and browser experience.

- Build a dataset lineage register: controlling tracker tab, approved runtime extract, transformation, checksum, consumer and synthetic-data notice.

- Standardise baseline sensor fields: temperature_c, pressure_bar, vibration_mm_s, flow_rate_kg_s, rotation_rpm and health_score where applicable.

- Replace uncoordinated legacy-key dependencies with an explicit adapter or migration plan; keep temporary adapters labelled and tested.

- Select one What-If API contract for UI clients and add regression tests for the WP-07 zero-day and 45-day scenario.

- Define shared demo constants and data policies only where approved by Step 0 decisions.

GATE 1 EVIDENCE Automated contract tests, dataset-lineage table, confirmed source path for each runtime consumer, and a signed-off API payload example for Unity and Three.js.

## Step 2: Unity Primary Experience

| Required activity | Acceptance proof |
| --- | --- |
| Open and validate the Unity URP project and primary plant scene. | Recorded scene run and console result. |
| Verify 50 asset objects, correct asset identifiers and WP-07 selection. | Count/mapping check plus screenshot or test log. |
| Verify sensor streaming and green/amber/red colour updates. | Timestamped update/latency record below one second target. |
| Verify HUD values, synthetic disclaimer and trend display. | Play-mode screenshots and field check. |
| Repair and verify What-If slider with cost overlay. | Visible 0-day 34% and 45-day 68% / USD 122,400; response timing below two seconds. |
| Integrate schedule timeline once Step 4 is accepted. | Unity schedule panel demonstration. |

## Step 3: Failure Predictor And Monte Carlo Validation

This work must use the Step 0 approved model specification and data interpretation. The current local model is an implementation asset only; it is not baseline acceptance evidence.

| Track | Actions | Gate evidence |
| --- | --- | --- |
| LSTM | Train or validate the approved sequence/features, time-based split, class handling, calibration and inference packaging. | AUC-ROC above 0.82; calibration result; feature/config manifest; SavedModel and ONNX or approved equivalent. |
| Monte Carlo fitting | Fit Weibull parameters from approved Failure_History grouping and include approved sensor/maintenance covariates. | Fitted-parameter report linked to data lineage and code version. |
| Monte Carlo validation | Run 100 approved MC_Validation scenarios and measure calibration. | Brier score below 0.15 with reproducible run output. |
| Performance | Benchmark standard 10,000-scenario request on demo workstation. | Timing under five seconds with environment recorded. |
| Narrative reconciliation | Determine how the validated engine and official 34% to 68% story coexist. | Approved decision: calibrated scenario, model-calibrated output, or baseline revision. |

## Step 4: Scheduler And Work Orders

- Feed approved risk outputs, approved asset costs and approved inspection cost into the maintenance scheduler.

- Implement or verify crew availability, maintenance interval and equipment-interdependency constraints required by the source documents.

- Generate the 90-day schedule and demonstrate the intended three newly high-risk assets rather than an all-critical output.

- Create a top-five work-order payload in mock Maximo mode while IBM integration is paused; preserve a tested boundary for eventual live Maximo execution.

- Expose the approved schedule in Unity and, after completion, in the browser viewer.

GATE 4 EVIDENCE Deterministic scheduler test fixture, schedule output, top-five work-order payload, Unity display proof and confirmation that the documented scenario is reproduced.

## Step 5: Three.js Viewer And Anomaly AI

| Capability | MVP implementation requirement | Evidence |
| --- | --- | --- |
| Three.js viewer | Browser-accessible 3D viewer with navigation, 50 assets, live/synthetic sensor state colour coding and baseline disclaimers. | Browser demo recording/screenshots, latency check and deployment artifact. |
| CNN Anomaly AI | ResNet-18 style visual classifier using synthetic Unity screenshots with greater than 80% validation accuracy. | Training/config manifest, validation metric and UI alert proof. |
| Permitted fallback | If CNN is not delivered in MVP, rule-based red-state-duration detector clearly labelled as fallback. | Approved fallback decision and visible Unity/browser alert proof. |

## Step 6: IBM Integration Reactivation

This step is conditional. It remains in the target architecture but is not to be executed while the approved IBM hold remains active.

| Platform element | Verification when reactivated |
| --- | --- |
| Maximo MAS 9.1 APM / Monitor | Load approved 50 assets, configure channels and verify work-order creation. |
| Watson Studio / Watson ML | Train/deploy approved models or verify model deployment route and metadata. |
| Watson IoT / Event Streams | Verify sensor ingestion, Kafka processing and state delivery to visual clients. |
| OpenShift / API Connect | Deploy API/viewer services and capture externally accessible endpoint evidence. |

## Step 7: Acceptance And Demonstration Handover

The project manager should receive one acceptance pack before any client-facing positioning:

- Completed acceptance matrix against every requirement and target in the three governing documents.

- Recorded WP-07 demonstration flow: selection, 34% state, 45-day change to 68%, USD 122,400 expected cost, and recommendation.

- Scheduler scenario evidence with 90-day view and top-five work-order output.

- Synthetic-data disclaimer visible in all client-visible experiences and presentation materials.

- Decision register showing every approved interpretation, fallback or remaining limitation.

- Conditional production deployment proposal covering IBM integration and live SCADA migration only after approval.

# 5. Parallel Work Rules

Parallel work is permitted only where it cannot force unresolved product decisions. The following lanes may be assigned to local IDE agents or team members after their dependencies are met:

| Lane | Can start after | Permitted work | Must not do |
| --- | --- | --- | --- |
| Contract recovery | Step 0 cost/API decisions | Unity API payload fix and contract tests. | Change official demo figures. |
| Data alignment | Step 0 data decisions | Lineage, loaders and schema adapter tests. | Invent a corrected dataset without approval. |
| ML validation | LSTM specification selected | Reproducible training/evaluation/export. | Present unapproved hybrid model as baseline. |
| Unity QA | Canonical API available | Play-mode validation and visual evidence. | Count React UI as Unity acceptance. |
| Three.js delivery | Sensor/API contract stable | Browser twin implementation. | Substitute React cards for 3D viewer. |
| Scheduler recovery | Risk/cost policies approved | Deterministic scheduling and WO tests. | Tune narrative outputs without documented basis. |

# 6. Scope Boundary

REQUIRED NOW The five baseline agents, Unity experience, Three.js viewer, 50-asset synthetic GDC Kenya data path, WP-07 decision scenario, scheduler/work orders, acceptance evidence and retained IBM integration boundary.

SUPPORTING ONLY UNLESS APPROVED OTHERWISE React integration dashboard, Redis and TimescaleDB choices, extended natural-language experiences, additional reporting panels and local mock tooling. These may help delivery but do not replace baseline acceptance.

POST-MVP OR APPROVAL-DEPENDENT Live GDC operational data, expansion to all 180 wells, HoloLens linkage, OTShield integration, production commercial rollout and active IBM deployment while the platform hold remains in force.

# 7. Governance Cadence And Reporting

| Control | Frequency | Required record |
| --- | --- | --- |
| Decision review | Before any baseline-sensitive implementation | Decision Log entry approved by project owner. |
| Implementation checkpoint | At completion of each gate | Implementation Checklist status with dated evidence. |
| Metric verification | At model/simulation or UI acceptance runs | Reproducible output, environment and data version. |
| Demo readiness review | Before stakeholder demonstration | Acceptance pack and known-limitations sign-off. |
| Scope change control | Whenever a new feature or changed narrative is proposed | Classification as baseline implementation, supporting implementation, proposed extension or baseline revision. |

# 8. Immediate Next Actions

- Obtain project-manager confirmation of the three governing files and the five open decisions in Step 0.

- Repair and test the Unity What-If API contract while preserving the approved numerical scenario.

- Create and approve the dataset/cost lineage map before changing scheduler or model outputs.

- Choose the approved LSTM specification and create a reproducible validation work item.

- Once Steps 0 and 1 pass, run Unity play-mode acceptance for Scenario 1 and Scenario 2, then recover the scheduler for Scenario 3.

PLAN SUCCESS CONDITION OTDT work should move from code-presence claims to evidence-backed gate completion. The product is complete only when the required documentary narrative is demonstrable through the approved implementation path and all exceptions are recorded.